## Sheet1
[9 empty] | Weekend (Sat, Sun) |  |  |  |  | ▽ |  | Review for Trainee
Renesas Technical Training
 | time axis 2017-11-06 to 2018-01-04
[1] | [Basic Knowledge] | bar: 2017-11-06 to 2017-11-09
Dir
[1.1] | - Working style (mail writing, report and request) | bar: 2017-11-06
[1.2] | - Design flow overview | bar: 2017-11-07
[1.3] | - Chip structure overview | bar: 2017-11-07
[1.4] | - Project directory structure overview | bar: 2017-11-07
[1.5] | - Script (Csh, Perl, VIM, etc.) | bar: 2017-11-08
[1.6] | - Script LAB | bar: 2017-11-08 to 2017-11-10; 2017-11-13
[1.7] | - Excel, EoD | bar: 2017-11-09 to 2017-11-10; 2017-11-13 to 2017-11-16
[1.8] | - Introduce simple tool usage (Verdi, DC, dve) => Before Checker | bar: 2017-11-14
[1.9] | - Assertion (Tentative)
[2] | [Synthesis] [ECO] | bar: 2017-11-10; 2017-11-13 to 2017-11-16
Dir
[2.1] | - What is Synthesis? Its position in design flow | bar: 2017-11-10
[2.2] | - Input, Output, their effects | bar: 2017-11-10
[2.3] | - How to do: env, library, common options & their effects… | bar: 2017-11-10
[2.4] | - How to check synthesis report (timing, area, power,…), MASTER_CHK, FM log, etc. | bar: 2017-11-10
[2.5] | - Debug mode in synthesis phase | bar: 2017-11-10
[2.6] | - ECR registration and ECO command creation | bar: 2017-11-10
[2.7] | - LAB | bar: 2017-11-13 to 2017-11-15
[3] | [Checkers] | bar: 2017-11-17; 2017-11-20 to 2017-11-24
Dir
[3.1] | - DFTcheck | bar: 2017-11-17
[3.2] | - HLDRC | bar: 2017-11-20
[3.3] | - STAcheck | bar: 2017-11-21
[3.4] | - False check | bar: 2017-11-21
[3.5] | - LAB | bar: 2017-11-22 to 2017-11-24; 2017-11-27 to 2017-11-28
[4] | [Verification - CT] | bar: 2017-11-27 to 2017-11-30
Dir
[4.1] | - What is CT, its position in design flow? Input? Output? | bar: 2017-11-27
[4.2] | - Simulation environment, common options & its effect | bar: 2017-11-27
[4.3] | - How to check result: result.rtl.l, external dump, waveform, common errors & how to solve | bar: 2017-11-29
[4.4] | - Checklist, TM, test.ssc.l, mode pin | bar: 2017-11-29
[4.5] | - How to clean up TM folder | bar: 2017-11-29
[4.6] | - LAB | bar: 2017-11-30
[5] | [Common modules] | bar: 2017-12-01; 2017-12-04 to 2017-12-08; 2017-12-11 to 2017-12-15; 2017-12-18 to 2017-12-19
Dir
[5.1] | PFC & PAD | bar: 2017-12-01
LAB of PFC/PAD | bar: 2017-12-01
[5.2] | Gen3 Bus structure, address map, routing path | bar: 2017-12-04
Bus arbitration and how to debug, how to check actual signals | bar: 2017-12-04
AXI, APB (protocol) how to confirm AXI , APB checklist, bus related checklist | bar: 2017-12-04
LAB of BUS | bar: 2017-12-04
[5.3] | CPG, MSTP, Reset, power down mode & clock reset network | bar: 2017-12-05
LAB of CPG | bar: 2017-12-05
Review LAB result | bar: 2017-12-05
[5.4] | SHX core overview & instructions | bar: 2017-12-06
LAB of SHX core | bar: 2017-12-06
[5.5] | ARM core (CA57, CA53, CR7) overview & instructions | bar: 2017-12-07
LAB of ARM core | bar: 2017-12-07
[5.6] | Interrupt (ARM, SHX), exception handling routine | bar: 2017-12-08
LAB of Interrupt | bar: 2017-12-08
[5.7] | DMAC | bar: 2017-12-11
LAB of DMAC | bar: 2017-12-11
[5.8] | LIFEC | bar: 2017-12-12
LAB of LIFEC | bar: 2017-12-12
[5.9] | IPMMU | bar: 2017-12-14
LAB of IPMMU | bar: 2017-12-14
[5.10] | MFI | bar: 2017-12-15
LAB of MFI | bar: 2017-12-15
[5.11] | Others: Verification management sheet, RTL version confirmation | bar: 2017-12-18 to 2017-12-19
[6] | [Design] | bar: 2017-12-20 to 2017-12-22; 2017-12-25 to 2017-12-27
Dir
[6.1] | - DRBFM, design review, peer review | bar: 2017-12-20
- LAB
[6.2] | - Spec documentation, RTL coding, UT sim | bar: 2017-12-21 to 2017-12-22; 2017-12-25
- LAB
[7] | [STA] | bar: 2017-12-28 to 2017-12-29; 2018-01-01
Dir
[7.1] | - STA working flow | bar: 2017-12-28
[7.2] | - SDC constraint: clock table, ACspec, Individual, Async, Kobetsu, Timing ECO | bar: 2017-12-28
[7.3] | - LAB | bar: 2017-12-28 to 2017-12-29; 2018-01-01
[8] | [Tester] | bar: 2018-01-02 to 2018-01-04
Dir
[8.1] | - What is tester? Tester flow | bar: 2018-01-02
[8.2] | - How to prepare tester patterns | bar: 2018-01-02
[8.3] | - Function debugging | bar: 2018-01-02; 2018-01-04
REVIEW MILESTONE | bar: 2017-11-09; 2017-11-17; 2017-11-24; 2017-11-30; 2017-12-04; 2017-12-07; 2017-12-11; 2017-12-15; 2017-12-22; 2018-01-01; 2018-01-04
LAB
MATERIALS
VIDEO
REDMINE
INPUT
UNDERSTADING DOCUMENT
CHECK LIST
MEETING MINUTE
ACTION ITEM
OUTPUT